February 10, 2015

Agreement for concrete work at:

Residence

55 Loring Avenue

Mill Valley, Californa

Between:

Greg Bushey / Concrete Contractor

Ca. License. 439293

1805 Eastman Ln.

Petaluma, Ca.

Tel 415 898-6008 Cell 707 332-7826

Bryna Holland - Homeowner

15 Blanca Drive

Novato, Ca.

Tel: 415-314-8453

Scope:

1. Take out existing driveway and triangular section of entrance walkway (approx. 800 sq. ft. total)

2. Grade to proper depth for 5" of concrete.

3. Set forms and install continuous 1/2" reinforcing steel at 18" centers min. both directions. Minimum lap length of 20".

4. Install channel drain supplied by owner at base of driveway. Encase the drain on three sides with concrete and 5 full length, 1/2" reinforcing direction.

5. Dowel new concrete to existing concrete to control future offset from settlement.

6. Place new concrete so that top of concrete meets top of existing slabs and roads. Install deep cut control joints to control cracking. Finish driveway with washed and washed exposed finish and added color to darken. Finish walkway section with steel troweled finish to match existing.

7. Provide extra concrete for forms previously set for retaining curb in front of house.

Payments: Total Material and Labor $12,600.00

* 1/3 on start of project, removal of concrete: $4,200.00.
* 1/3 draw on completion of forms, rebar, install of drain. $4,200.00.
* balance on completion of project. $4,200.00

Completion Schedule: Complete work by Friday, February 20, 2015.

General Conditions:

1. If Contractor is injured in the course of performing the specified work, Homeowner shall be exempt from liability for such injuries to the fullest extent allowed by law. If subcontractors are injured in the course of performing the specified work, Homeowner shall be exempt from liability for such injuries to the fullest extent allowed by law.

2. Contractor agrees that final payment shall be withheld by Homeowner until Contractor presents Homeowner with any applicable lien waivers, releases, or acknowledgment of full payment from each subcontractor.

3. If any dispute arises under the terms of this agreement, the parties agree to select a mutually agreeable neutral third party to help them mediate it. If the mediation is deemed unsuccessful, the parties agree that the dispute shall be decided by the applicable small claims.

4. Contractor agrees to hold harmless and indemnify Homeowner for all damages, costs and attorney fees that arise out of harm caused to Contractor, subcontractors and other third parties, known and unknown, by Contractor's performance of the specified work.

Respectfully submitted,

Greg Bushey

Accepted:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_